## Project Workflow Stages
Record ID | Project | Stage Sequence | Stage Name | Predecessor Stage | Dependency Type | Lag Days | Department | Workflow Status | Planned Hours | Completed Hours | Remarks
931c8fb1-d8ee-4667-8e50-2db514f1c8c7 | 24-2543 - Berluti Facade - MOE | 1 | PPO JOINERY |  | Finish-to-Start (FS) | 0 | PPO JOINERY (PPO-JOINERY) | In Progress (IN_PROGRESS) | 120 | 0 | Resources Assigned: 4
9acb8025-c93b-436a-af1b-48bc0e50eb02 | 24-2543 - Berluti Facade - MOE | 2 | PPO METAL |  | Finish-to-Start (FS) | 0 | PPO METAL (PPO-METAL) | Not Started (NOT_STARTED) | 120 | 0 | Generated from SPAA - SIMPLE
f039a516-f0cf-41d8-bbfe-ef0b126094d9 | 24-2543 - Berluti Facade - MOE | 3 | MACHINE SHOP |  | Finish-to-Start (FS) | 0 | MACHINE SHOP (MACHINE-SHOP) | Not Started (NOT_STARTED) | 100 | 0 | Generated from SPAA - SIMPLE
4a3de622-d458-4fa6-844c-5ce808d308d9 | 24-2543 - Berluti Facade - MOE | 4 | MDF STRUCTURE PERMANENT |  | Finish-to-Start (FS) | 0 | MDF STRUCTURE PERMANENT (MDF-STR-PER) | Not Started (NOT_STARTED) | 100 | 0 | Generated from SPAA - SIMPLE
5e8915c2-d979-41e3-82ab-9afd4ab55770 | 24-2543 - Berluti Facade - MOE | 5 | MDF STRUCTURE SPAA |  | Finish-to-Start (FS) | 0 | MDF STRUCTURE SPAA (MDF-STR-SPAA) | Not Started (NOT_STARTED) | 100 | 0 | Generated from SPAA - SIMPLE
b19151d9-c83e-4083-9558-246cda8f27da | 24-2543 - Berluti Facade - MOE | 6 | METAL FAB |  | Finish-to-Start (FS) | 0 | METAL FAB (METAL-FAB) | Not Started (NOT_STARTED) | 100 | 0 | Generated from SPAA - SIMPLE
8953a232-f837-4424-9615-975a751db888 | 24-2543 - Berluti Facade - MOE | 7 | METAL POLISH |  | Finish-to-Start (FS) | 0 | METAL POLISH (METAL-POLISH) | Not Started (NOT_STARTED) | 100 | 0 | Generated from SPAA - SIMPLE
261fc73c-7033-4b03-894f-807c4f4a298b | 24-2543 - Berluti Facade - MOE | 8 | PAINT |  | Finish-to-Start (FS) | 0 | PAINT (PAINT) | Not Started (NOT_STARTED) | 100 | 0 | Generated from SPAA - SIMPLE
22d390a8-c1fd-474e-8b2f-e4040fb83951 | 24-2543 - Berluti Facade - MOE | 9 | ACRYLIC |  | Finish-to-Start (FS) | 0 | ACRYLIC (ACRYLIC) | Not Started (NOT_STARTED) | 100 | 0 | Generated from SPAA - SIMPLE
87c14396-991c-41b5-ad3a-f86a3b3667cb | 24-2543 - Berluti Facade - MOE | 10 | ELECTRICAL |  | Finish-to-Start (FS) | 0 | ELECTRICAL (ELECTRICAL) | Not Started (NOT_STARTED) | 100 | 0 | Generated from SPAA - SIMPLE
7161b8dd-f4ac-44e5-a955-818d19b9dc54 | 24-2543 - Berluti Facade - MOE | 11 | PRINT |  | Finish-to-Start (FS) | 0 | PRINT (PRINT) | Not Started (NOT_STARTED) | 100 | 0 | Generated from SPAA - SIMPLE
a308fc8d-a4ff-491c-8fb0-0e288165b542 | 24-2543 - Berluti Facade - MOE | 12 | MDF FINAL PERMANENT |  | Finish-to-Start (FS) | 0 | MDF FINAL PERMANENT (MDF-FIN-PER) | Not Started (NOT_STARTED) | 100 | 0 | Generated from SPAA - SIMPLE
53f81824-e924-41db-a2fb-62186d6745d3 | 24-2543 - Berluti Facade - MOE | 13 | MDF FINAL SPAA |  | Finish-to-Start (FS) | 0 | MDF FINAL SPAA (MDF-FIN-SPA) | Not Started (NOT_STARTED) | 100 | 0 | Generated from SPAA - SIMPLE
83ea743a-310d-436e-9c6c-b93de0cbbeff | 24-2543 - Berluti Facade - MOE | 14 | INSTALLATION |  | Finish-to-Start (FS) | 0 | INSTALLATION (INSTALLATION) | Not Started (NOT_STARTED) | 100 | 0 | Generated from SPAA - SIMPLE
a75e6219-d389-400c-b05a-d5f2d16d73ac | 24-3211 - BVLGARI ghana Accra Scentopia | 1 | PPO JOINERY |  | Finish-to-Start (FS) | 0 | PPO JOINERY (PPO-JOINERY) | Waiting (WAITING) | 8 | 7.84
a7ea1906-bfc2-4f09-a4f7-db4b887d080c | 24-3211 - BVLGARI ghana Accra Scentopia | 2 | PPO METAL |  | Finish-to-Start (FS) | 0 | PPO METAL (PPO-METAL) | Not Started (NOT_STARTED) | 8 | 0 | Generated from SPAA-FIXED - SIMPLE
3f04aae7-ec2b-4623-8e25-1554e457ab7f | 24-3211 - BVLGARI ghana Accra Scentopia | 3 | MACHINE SHOP |  | Finish-to-Start (FS) | 0 | MACHINE SHOP (MACHINE-SHOP) | Not Started (NOT_STARTED) | 8 | 0
87c3e86f-8c71-4eef-b618-92a5ee3a4e1b | 24-3211 - BVLGARI ghana Accra Scentopia | 4 | MDF STRUCTURE PERMANENT |  | Finish-to-Start (FS) | 0 | MDF STRUCTURE PERMANENT (MDF-STR-PER) | Not Started (NOT_STARTED) | 8 | 0 | Generated from SPAA-FIXED - SIMPLE
255d13d3-3ce3-4eba-953b-6531833f5f46 | 24-3211 - BVLGARI ghana Accra Scentopia | 5 | MDF STRUCTURE SPAA |  | Finish-to-Start (FS) | 0 | MDF STRUCTURE SPAA (MDF-STR-SPAA) | Not Started (NOT_STARTED) | 8 | 0 | Generated from SPAA-FIXED - SIMPLE
31bd4bc5-0d1a-417c-8ee6-b8d3ec3c006f | 24-3211 - BVLGARI ghana Accra Scentopia | 6 | METAL FAB |  | Finish-to-Start (FS) | 0 | METAL FAB (METAL-FAB) | Not Started (NOT_STARTED) | 8 | 0 | Generated from SPAA-FIXED - SIMPLE
5fc6cf22-7d64-4b6e-9545-80eb096a6831 | 24-3211 - BVLGARI ghana Accra Scentopia | 7 | METAL POLISH |  | Finish-to-Start (FS) | 0 | METAL POLISH (METAL-POLISH) | Not Started (NOT_STARTED) | 8 | 0 | Generated from SPAA-FIXED - SIMPLE
53e4c175-a920-4ab9-b033-1eb7a3fe3925 | 24-3211 - BVLGARI ghana Accra Scentopia | 8 | PAINT |  | Finish-to-Start (FS) | 0 | PAINT (PAINT) | Not Started (NOT_STARTED) | 8 | 0 | Generated from SPAA-FIXED - SIMPLE
2ac3f650-50f4-4e9a-808c-265dac7216fd | 24-3211 - BVLGARI ghana Accra Scentopia | 9 | ACRYLIC |  | Finish-to-Start (FS) | 0 | ACRYLIC (ACRYLIC) | Not Started (NOT_STARTED) | 8 | 0 | Generated from SPAA-FIXED - SIMPLE
df342b3f-87ec-48f7-8a6e-27fd80222113 | 24-3211 - BVLGARI ghana Accra Scentopia | 10 | ELECTRICAL |  | Finish-to-Start (FS) | 0 | ELECTRICAL (ELECTRICAL) | Not Started (NOT_STARTED) | 8 | 0 | Generated from SPAA-FIXED - SIMPLE
4c8e8742-96ad-458e-b378-d5876dde0215 | 24-3211 - BVLGARI ghana Accra Scentopia | 11 | PRINT |  | Finish-to-Start (FS) | 0 | PRINT (PRINT) | Not Started (NOT_STARTED) | 8 | 0 | Generated from SPAA-FIXED - SIMPLE
221321cf-1829-4c85-87a1-2964fe83a559 | 24-3211 - BVLGARI ghana Accra Scentopia | 12 | MDF FINAL PERMANENT |  | Finish-to-Start (FS) | 0 | MDF FINAL PERMANENT (MDF-FIN-PER) | Not Started (NOT_STARTED) | 8 | 0 | Generated from SPAA-FIXED - SIMPLE
e9a58e3e-7f06-4e00-a592-fe5943b78522 | 24-3211 - BVLGARI ghana Accra Scentopia | 13 | MDF FINAL SPAA |  | Finish-to-Start (FS) | 0 | MDF FINAL SPAA (MDF-FIN-SPA) | Not Started (NOT_STARTED) | 8 | 0 | Generated from SPAA-FIXED - SIMPLE
49f57570-8d35-453f-bffd-89849eb66213 | 24-3211 - BVLGARI ghana Accra Scentopia | 14 | INSTALLATION |  | Finish-to-Start (FS) | 0 | INSTALLATION (INSTALLATION) | Not Started (NOT_STARTED) | 8 | 0 | Generated from SPAA-FIXED - SIMPLE
6dbd1978-00c3-422c-9710-46fbaa175e04 | 24-3078 - Pernod Ricard deal, Bahrain Duty Free | 1 | PPO JOINERY |  | Finish-to-Start (FS) | 0 | PPO JOINERY (PPO-JOINERY) | Complete (COMPLETE) | 0 | 100 | Generated from PERMANENT - MEDIUM
c7ff323f-657b-4a4d-9c07-2378f2892965 | 24-3078 - Pernod Ricard deal, Bahrain Duty Free | 2 | PPO METAL | 24-3078 - Pernod Ricard deal, Bahrain Duty Free ¦ 1. PPO JOINERY | Finish-to-Start (FS) | 0 | PPO METAL (PPO-METAL) | In Progress (IN_PROGRESS) | 120 | 0 | Resources Assigned: 4
b46db45b-b39b-4bcf-95c1-24f6995bcbc0 | 24-3078 - Pernod Ricard deal, Bahrain Duty Free | 3 | MACHINE SHOP | 24-3078 - Pernod Ricard deal, Bahrain Duty Free ¦ 2. PPO METAL | Finish-to-Start (FS) | 0 | MACHINE SHOP (MACHINE-SHOP) | Not Started (NOT_STARTED) | 100 | 0 | Generated from PERMANENT - MEDIUM
73fdffd7-ce2c-4dc6-8bf5-6acce0c9e74e | 24-3078 - Pernod Ricard deal, Bahrain Duty Free | 4 | MDF STRUCTURE PERMANENT | 24-3078 - Pernod Ricard deal, Bahrain Duty Free ¦ 3. MACHINE SHOP | Finish-to-Start (FS) | 0 | MDF STRUCTURE PERMANENT (MDF-STR-PER) | Not Started (NOT_STARTED) | 100 | 0 | Generated from PERMANENT - MEDIUM
323c1c3b-928c-4737-8dfa-a73d32f54d8b | 24-3078 - Pernod Ricard deal, Bahrain Duty Free | 5 | MDF STRUCTURE SPAA | 24-3078 - Pernod Ricard deal, Bahrain Duty Free ¦ 4. MDF STRUCTURE PERMANENT | Finish-to-Start (FS) | 0 | MDF STRUCTURE SPAA (MDF-STR-SPAA) | Not Started (NOT_STARTED) | 100 | 0 | Generated from PERMANENT - MEDIUM
93c2cf55-4ea6-43ea-8fe3-fab007a9c94d | 24-3078 - Pernod Ricard deal, Bahrain Duty Free | 6 | METAL FAB | 24-3078 - Pernod Ricard deal, Bahrain Duty Free ¦ 5. MDF STRUCTURE SPAA | Finish-to-Start (FS) | 0 | METAL FAB (METAL-FAB) | Not Started (NOT_STARTED) | 100 | 0 | Generated from PERMANENT - MEDIUM
71b6561b-9db3-4f55-b352-5c98ecaf9b58 | 24-3078 - Pernod Ricard deal, Bahrain Duty Free | 7 | METAL POLISH | 24-3078 - Pernod Ricard deal, Bahrain Duty Free ¦ 6. METAL FAB | Finish-to-Start (FS) | 0 | METAL POLISH (METAL-POLISH) | Not Started (NOT_STARTED) | 100 | 0 | Generated from PERMANENT - MEDIUM
dacd2ac2-9846-43a6-be66-e40a623f2137 | 24-3078 - Pernod Ricard deal, Bahrain Duty Free | 8 | PAINT | 24-3078 - Pernod Ricard deal, Bahrain Duty Free ¦ 7. METAL POLISH | Finish-to-Start (FS) | 0 | PAINT (PAINT) | Not Started (NOT_STARTED) | 100 | 0 | Generated from PERMANENT - MEDIUM
2f118181-d0e0-4c5c-bd46-bf64bcdb5e81 | 24-3078 - Pernod Ricard deal, Bahrain Duty Free | 9 | ACRYLIC | 24-3078 - Pernod Ricard deal, Bahrain Duty Free ¦ 8. PAINT | Finish-to-Start (FS) | 0 | ACRYLIC (ACRYLIC) | Not Started (NOT_STARTED) | 100 | 0 | Generated from PERMANENT - MEDIUM
7944e068-0d94-4fcb-b3a4-c206356a0428 | 24-3078 - Pernod Ricard deal, Bahrain Duty Free | 10 | ELECTRICAL | 24-3078 - Pernod Ricard deal, Bahrain Duty Free ¦ 9. ACRYLIC | Finish-to-Start (FS) | 0 | ELECTRICAL (ELECTRICAL) | Not Started (NOT_STARTED) | 100 | 0 | Generated from PERMANENT - MEDIUM
0b3c07b2-bd4e-405c-88a4-6f9dbf07704f | 24-3078 - Pernod Ricard deal, Bahrain Duty Free | 11 | PRINT | 24-3078 - Pernod Ricard deal, Bahrain Duty Free ¦ 10. ELECTRICAL | Finish-to-Start (FS) | 0 | PRINT (PRINT) | Not Started (NOT_STARTED) | 100 | 0 | Generated from PERMANENT - MEDIUM
007a6fff-cc94-437e-92f7-d36a234161e9 | 24-3078 - Pernod Ricard deal, Bahrain Duty Free | 12 | MDF FINAL PERMANENT | 24-3078 - Pernod Ricard deal, Bahrain Duty Free ¦ 11. PRINT | Finish-to-Start (FS) | 0 | MDF FINAL PERMANENT (MDF-FIN-PER) | Not Started (NOT_STARTED) | 100 | 0 | Generated from PERMANENT - MEDIUM
47c9758f-8822-46db-858b-de4722412cfe | 24-3078 - Pernod Ricard deal, Bahrain Duty Free | 13 | MDF FINAL SPAA | 24-3078 - Pernod Ricard deal, Bahrain Duty Free ¦ 12. MDF FINAL PERMANENT | Finish-to-Start (FS) | 0 | MDF FINAL SPAA (MDF-FIN-SPA) | Not Started (NOT_STARTED) | 100 | 0 | Generated from PERMANENT - MEDIUM
e3699596-2103-43db-a0a7-f713a99b5e52 | 24-3078 - Pernod Ricard deal, Bahrain Duty Free | 14 | INSTALLATION | 24-3078 - Pernod Ricard deal, Bahrain Duty Free ¦ 13. MDF FINAL SPAA | Finish-to-Start (FS) | 0 | INSTALLATION (INSTALLATION) | Not Started (NOT_STARTED) | 100 | 0 | Generated from PERMANENT - MEDIUM
3e239d51-f785-4e9e-9039-071bd62295e1 | 24-3239 - EL- CL - ZINO CAP SUD, IVORY COAST | 1 | PPO JOINERY |  | Finish-to-Start (FS) | 0 | PPO JOINERY (PPO-JOINERY) | Waiting (WAITING) | 8 | 7.84
23b6ddb8-da0a-4126-87ed-9996b5877ad0 | 24-3239 - EL- CL - ZINO CAP SUD, IVORY COAST | 2 | PPO METAL |  | Finish-to-Start (FS) | 0 | PPO METAL (PPO-METAL) | Not Started (NOT_STARTED) | 8 | 0 | Generated from PERMANENT - COMPLEX
fab6bc99-6fe5-4b51-8e5a-24ae1a9dafc0 | 24-3239 - EL- CL - ZINO CAP SUD, IVORY COAST | 3 | MACHINE SHOP |  | Finish-to-Start (FS) | 0 | MACHINE SHOP (MACHINE-SHOP) | Not Started (NOT_STARTED) | 8 | 0 | Generated from PERMANENT - COMPLEX
a4ee3c95-6bcc-4bae-a31f-5fdc7829bf51 | 24-3239 - EL- CL - ZINO CAP SUD, IVORY COAST | 4 | MDF STRUCTURE PERMANENT |  | Finish-to-Start (FS) | 0 | MDF STRUCTURE PERMANENT (MDF-STR-PER) | Not Started (NOT_STARTED) | 8 | 0 | Generated from PERMANENT - COMPLEX
8714d113-d72a-461a-a37b-bbc48b846396 | 24-3239 - EL- CL - ZINO CAP SUD, IVORY COAST | 5 | MDF STRUCTURE SPAA |  | Finish-to-Start (FS) | 0 | MDF STRUCTURE SPAA (MDF-STR-SPAA) | Not Started (NOT_STARTED) | 8 | 0
5f57e866-76ed-4c3a-b3b8-4cee08d080a0 | 24-3239 - EL- CL - ZINO CAP SUD, IVORY COAST | 6 | METAL FAB |  | Finish-to-Start (FS) | 0 | METAL FAB (METAL-FAB) | Not Started (NOT_STARTED) | 8 | 0 | Generated from PERMANENT - COMPLEX
40a91ceb-258b-4e39-840f-eef5c5bdd7a7 | 24-3239 - EL- CL - ZINO CAP SUD, IVORY COAST | 7 | METAL POLISH |  | Finish-to-Start (FS) | 0 | METAL POLISH (METAL-POLISH) | Not Started (NOT_STARTED) | 8 | 0 | Generated from PERMANENT - COMPLEX
c792cb9b-505c-4119-848a-7c85c99dc147 | 24-3239 - EL- CL - ZINO CAP SUD, IVORY COAST | 8 | PAINT |  | Finish-to-Start (FS) | 0 | PAINT (PAINT) | Not Started (NOT_STARTED) | 8 | 0 | Generated from PERMANENT - COMPLEX
e2b63b88-be65-43a2-a4cc-d657747dbfee | 24-3239 - EL- CL - ZINO CAP SUD, IVORY COAST | 9 | ACRYLIC |  | Finish-to-Start (FS) | 0 | ACRYLIC (ACRYLIC) | Not Started (NOT_STARTED) | 8 | 0 | Generated from PERMANENT - COMPLEX
1fc948f8-ae4b-4510-9c16-81bdd6fd251d | 24-3239 - EL- CL - ZINO CAP SUD, IVORY COAST | 10 | ELECTRICAL |  | Finish-to-Start (FS) | 0 | ELECTRICAL (ELECTRICAL) | Not Started (NOT_STARTED) | 8 | 0 | Generated from PERMANENT - COMPLEX
e8d13ff7-9ab0-4a16-83f6-acb8e9e5c1e8 | 24-3239 - EL- CL - ZINO CAP SUD, IVORY COAST | 11 | PRINT |  | Finish-to-Start (FS) | 0 | PRINT (PRINT) | Not Started (NOT_STARTED) | 8 | 0 | Generated from PERMANENT - COMPLEX
f982df1b-2c39-42af-a54a-79af2346e607 | 24-3239 - EL- CL - ZINO CAP SUD, IVORY COAST | 12 | MDF FINAL PERMANENT |  | Finish-to-Start (FS) | 0 | MDF FINAL PERMANENT (MDF-FIN-PER) | Not Started (NOT_STARTED) | 8 | 0 | Generated from PERMANENT - COMPLEX
3f045b8d-6457-44f6-8474-68484a270ff9 | 24-3239 - EL- CL - ZINO CAP SUD, IVORY COAST | 13 | MDF FINAL SPAA |  | Finish-to-Start (FS) | 0 | MDF FINAL SPAA (MDF-FIN-SPA) | Not Started (NOT_STARTED) | 8 | 0 | Generated from PERMANENT - COMPLEX
7ac063b9-d840-4d23-8975-fbc3d32c04a2 | 24-3239 - EL- CL - ZINO CAP SUD, IVORY COAST | 14 | INSTALLATION |  | Finish-to-Start (FS) | 0 | INSTALLATION (INSTALLATION) | Not Started (NOT_STARTED) | 8 | 0 | Generated from PERMANENT - COMPLEX
70d3c16b-4d8a-4486-b6e6-b183ac4e40cd | 24-3212 - Bvlari_GHANA Accra Scentopia Kempinski | 1 | PPO JOINERY |  | Finish-to-Start (FS) | 0 | PPO JOINERY (PPO-JOINERY) | Waiting (WAITING) | 8 | 7.84
f1fc86ac-f43e-4dfc-9381-5d9b8efc04c0 | 24-3212 - Bvlari_GHANA Accra Scentopia Kempinski | 2 | PPO METAL |  | Finish-to-Start (FS) | 0 | PPO METAL (PPO-METAL) | Not Started (NOT_STARTED) | 8 | 0 | Generated from PERMANENT - MEDIUM
bb39f142-0257-4e67-85d1-9dd097370e3e | 24-3212 - Bvlari_GHANA Accra Scentopia Kempinski | 3 | MACHINE SHOP |  | Finish-to-Start (FS) | 0 | MACHINE SHOP (MACHINE-SHOP) | Not Started (NOT_STARTED) | 8 | 0
d6434c37-566e-4361-b791-7411f0fa6beb | 24-3212 - Bvlari_GHANA Accra Scentopia Kempinski | 4 | MDF STRUCTURE PERMANENT |  | Finish-to-Start (FS) | 0 | MDF STRUCTURE PERMANENT (MDF-STR-PER) | Not Started (NOT_STARTED) | 8 | 0 | Generated from PERMANENT - MEDIUM
7cfe4d98-dcf7-4e6b-9872-3c7de7a721de | 24-3212 - Bvlari_GHANA Accra Scentopia Kempinski | 5 | MDF STRUCTURE SPAA |  | Finish-to-Start (FS) | 0 | MDF STRUCTURE SPAA (MDF-STR-SPAA) | Not Started (NOT_STARTED) | 8 | 0 | Generated from PERMANENT - MEDIUM
bee3fac9-b19c-4fd8-aba7-c8dd7fdf5119 | 24-3212 - Bvlari_GHANA Accra Scentopia Kempinski | 6 | METAL FAB |  | Finish-to-Start (FS) | 0 | METAL FAB (METAL-FAB) | Not Started (NOT_STARTED) | 8 | 0 | Generated from PERMANENT - MEDIUM
4902ec88-aaec-4ee2-9a86-f29b2701fa72 | 24-3212 - Bvlari_GHANA Accra Scentopia Kempinski | 7 | METAL POLISH |  | Finish-to-Start (FS) | 0 | METAL POLISH (METAL-POLISH) | Not Started (NOT_STARTED) | 8 | 0 | Generated from PERMANENT - MEDIUM
8b7d05cf-4bfa-4f0a-a275-b79a3504a046 | 24-3212 - Bvlari_GHANA Accra Scentopia Kempinski | 8 | PAINT |  | Finish-to-Start (FS) | 0 | PAINT (PAINT) | Not Started (NOT_STARTED) | 8 | 0 | Generated from PERMANENT - MEDIUM
68f62808-914a-40d6-8a57-e09ff753c1c4 | 24-3212 - Bvlari_GHANA Accra Scentopia Kempinski | 9 | ACRYLIC |  | Finish-to-Start (FS) | 0 | ACRYLIC (ACRYLIC) | Not Started (NOT_STARTED) | 8 | 0 | Generated from PERMANENT - MEDIUM
2bfacc54-3baa-47b9-b339-ebaf10373041 | 24-3212 - Bvlari_GHANA Accra Scentopia Kempinski | 10 | ELECTRICAL |  | Finish-to-Start (FS) | 0 | ELECTRICAL (ELECTRICAL) | Not Started (NOT_STARTED) | 8 | 0 | Generated from PERMANENT - MEDIUM
09b47c83-ad73-4e87-9c31-224b94baf9df | 24-3212 - Bvlari_GHANA Accra Scentopia Kempinski | 11 | PRINT |  | Finish-to-Start (FS) | 0 | PRINT (PRINT) | Not Started (NOT_STARTED) | 8 | 0 | Generated from PERMANENT - MEDIUM
169a602f-2434-4143-a504-5af8d260cbdc | 24-3212 - Bvlari_GHANA Accra Scentopia Kempinski | 12 | MDF FINAL PERMANENT |  | Finish-to-Start (FS) | 0 | MDF FINAL PERMANENT (MDF-FIN-PER) | Not Started (NOT_STARTED) | 8 | 0 | Generated from PERMANENT - MEDIUM
9bfe05d3-8989-4d11-a8ea-7dba2bf9ef1a | 24-3212 - Bvlari_GHANA Accra Scentopia Kempinski | 13 | MDF FINAL SPAA |  | Finish-to-Start (FS) | 0 | MDF FINAL SPAA (MDF-FIN-SPA) | Not Started (NOT_STARTED) | 8 | 0 | Generated from PERMANENT - MEDIUM
b31ffb82-d968-435b-a8de-21f5f5721973 | 24-3212 - Bvlari_GHANA Accra Scentopia Kempinski | 14 | INSTALLATION |  | Finish-to-Start (FS) | 0 | INSTALLATION (INSTALLATION) | Not Started (NOT_STARTED) | 8 | 0 | Generated from PERMANENT - MEDIUM
0051b6b0-05a0-46d1-9fd2-a7695d638a6e | 24-3365 - PEN_T3 SHOP 700 Egypt_30th AUG | 1 | PPO JOINERY |  | Finish-to-Start (FS) | 0 | PPO JOINERY (PPO-JOINERY) | Waiting (WAITING) | 8 | 7.84
2da60ba7-ea48-47c4-b381-015806813ff5 | 24-3365 - PEN_T3 SHOP 700 Egypt_30th AUG | 2 | PPO METAL |  | Finish-to-Start (FS) | 0 | PPO METAL (PPO-METAL) | Not Started (NOT_STARTED) | 8 | 0 | Generated from PERMANENT - SIMPLE
85b99b36-72aa-43ba-bdbf-1ca3c86a8d79 | 24-3365 - PEN_T3 SHOP 700 Egypt_30th AUG | 3 | MACHINE SHOP |  | Finish-to-Start (FS) | 0 | MACHINE SHOP (MACHINE-SHOP) | Not Started (NOT_STARTED) | 8 | 0 | Generated from PERMANENT - SIMPLE
6fda5a62-fc4c-4bbe-bda7-a7c139bda82d | 24-3365 - PEN_T3 SHOP 700 Egypt_30th AUG | 4 | MDF STRUCTURE PERMANENT |  | Finish-to-Start (FS) | 0 | MDF STRUCTURE PERMANENT (MDF-STR-PER) | Not Started (NOT_STARTED) | 8 | 0 | Generated from PERMANENT - SIMPLE
8e72b7ac-4176-41bc-ad6c-451fca70b313 | 24-3365 - PEN_T3 SHOP 700 Egypt_30th AUG | 5 | MDF STRUCTURE SPAA |  | Finish-to-Start (FS) | 0 | MDF STRUCTURE SPAA (MDF-STR-SPAA) | Not Started (NOT_STARTED) | 8 | 0 | Generated from PERMANENT - SIMPLE
cce69686-efc7-4f7e-ba02-5c6adcf04032 | 24-3365 - PEN_T3 SHOP 700 Egypt_30th AUG | 6 | METAL FAB |  | Finish-to-Start (FS) | 0 | METAL FAB (METAL-FAB) | Not Started (NOT_STARTED) | 8 | 0 | Generated from PERMANENT - SIMPLE
36230513-e334-49aa-8fc5-6febbcf22dc6 | 24-3365 - PEN_T3 SHOP 700 Egypt_30th AUG | 7 | METAL POLISH |  | Finish-to-Start (FS) | 0 | METAL POLISH (METAL-POLISH) | Not Started (NOT_STARTED) | 8 | 0 | Generated from PERMANENT - SIMPLE
ca73e096-fe03-47af-a87d-d6557bd08b85 | 24-3365 - PEN_T3 SHOP 700 Egypt_30th AUG | 8 | PAINT |  | Finish-to-Start (FS) | 0 | PAINT (PAINT) | Not Started (NOT_STARTED) | 8 | 0 | Generated from PERMANENT - SIMPLE
48488bdf-d746-4062-9b6b-064e56bc5f2c | 24-3365 - PEN_T3 SHOP 700 Egypt_30th AUG | 9 | ACRYLIC |  | Finish-to-Start (FS) | 0 | ACRYLIC (ACRYLIC) | Not Started (NOT_STARTED) | 8 | 0 | Generated from PERMANENT - SIMPLE
26d09694-4c93-46a8-9bc5-34b76a5ea328 | 24-3365 - PEN_T3 SHOP 700 Egypt_30th AUG | 10 | ELECTRICAL |  | Finish-to-Start (FS) | 0 | ELECTRICAL (ELECTRICAL) | Not Started (NOT_STARTED) | 8 | 0
6496c8dd-4b85-4bc3-8c50-6d9df13f2990 | 24-3365 - PEN_T3 SHOP 700 Egypt_30th AUG | 11 | PRINT |  | Finish-to-Start (FS) | 0 | PRINT (PRINT) | Not Started (NOT_STARTED) | 8 | 0 | Generated from PERMANENT - SIMPLE
d375d7f7-9d02-4d61-98bc-1b2d0f51b308 | 24-3365 - PEN_T3 SHOP 700 Egypt_30th AUG | 12 | MDF FINAL PERMANENT |  | Finish-to-Start (FS) | 0 | MDF FINAL PERMANENT (MDF-FIN-PER) | Not Started (NOT_STARTED) | 8 | 0 | Generated from PERMANENT - SIMPLE
b35a0742-3c7a-41fb-8384-e573c8195715 | 24-3365 - PEN_T3 SHOP 700 Egypt_30th AUG | 13 | MDF FINAL SPAA |  | Finish-to-Start (FS) | 0 | MDF FINAL SPAA (MDF-FIN-SPA) | Not Started (NOT_STARTED) | 8 | 0 | Generated from PERMANENT - SIMPLE
5fc290e3-1445-4126-bf7e-f825374d457c | 24-3365 - PEN_T3 SHOP 700 Egypt_30th AUG | 14 | INSTALLATION |  | Finish-to-Start (FS) | 0 | INSTALLATION (INSTALLATION) | Not Started (NOT_STARTED) | 8 | 0 | Generated from PERMANENT - SIMPLE
50837c2e-c745-4510-bce4-dc040e74fc76 | 24-3429 - GUCCI, BBY and BOSS - Personalization BW, Kenya | 1 | PPO JOINERY |  | Finish-to-Start (FS) | 0 | PPO JOINERY (PPO-JOINERY) | Waiting (WAITING) | 8 | 7.84
ce3369d5-cdf0-47e1-8285-65de0d3dde55 | 24-3429 - GUCCI, BBY and BOSS - Personalization BW, Kenya | 2 | PPO METAL |  | Finish-to-Start (FS) | 0 | PPO METAL (PPO-METAL) | Not Started (NOT_STARTED) | 8 | 0 | Generated from SPAA - MEDIUM
79770f36-be82-482c-834b-d84fb3abd6d1 | 24-3429 - GUCCI, BBY and BOSS - Personalization BW, Kenya | 3 | MACHINE SHOP |  | Finish-to-Start (FS) | 0 | MACHINE SHOP (MACHINE-SHOP) | Not Started (NOT_STARTED) | 8 | 0 | Generated from SPAA - MEDIUM
2edd2c2d-963a-45bc-89d3-71cf079db2ac | 24-3429 - GUCCI, BBY and BOSS - Personalization BW, Kenya | 4 | MDF STRUCTURE PERMANENT |  | Finish-to-Start (FS) | 0 | MDF STRUCTURE PERMANENT (MDF-STR-PER) | Not Started (NOT_STARTED) | 8 | 0 | Generated from SPAA - MEDIUM
3a2367ce-08a0-436a-a3cc-22d8bf4699af | 24-3429 - GUCCI, BBY and BOSS - Personalization BW, Kenya | 5 | MDF STRUCTURE SPAA |  | Finish-to-Start (FS) | 0 | MDF STRUCTURE SPAA (MDF-STR-SPAA) | Not Started (NOT_STARTED) | 8 | 0 | Generated from SPAA - MEDIUM
95b4cef7-cdff-4b9e-be8e-6b69e7b2fbab | 24-3429 - GUCCI, BBY and BOSS - Personalization BW, Kenya | 6 | METAL FAB |  | Finish-to-Start (FS) | 0 | METAL FAB (METAL-FAB) | Not Started (NOT_STARTED) | 8 | 0 | Generated from SPAA - MEDIUM
7eac306d-3be2-42c1-9dfa-8049852fee72 | 24-3429 - GUCCI, BBY and BOSS - Personalization BW, Kenya | 7 | METAL POLISH |  | Finish-to-Start (FS) | 0 | METAL POLISH (METAL-POLISH) | Not Started (NOT_STARTED) | 8 | 0 | Generated from SPAA - MEDIUM
807ac9af-848f-4b1c-aa7e-1c6aeb7881bd | 24-3429 - GUCCI, BBY and BOSS - Personalization BW, Kenya | 8 | PAINT |  | Finish-to-Start (FS) | 0 | PAINT (PAINT) | Not Started (NOT_STARTED) | 8 | 0 | Generated from SPAA - MEDIUM
287c3f1b-4f75-4d12-bad1-da665061a493 | 24-3429 - GUCCI, BBY and BOSS - Personalization BW, Kenya | 9 | ACRYLIC |  | Finish-to-Start (FS) | 0 | ACRYLIC (ACRYLIC) | Not Started (NOT_STARTED) | 8 | 0 | Generated from SPAA - MEDIUM
7776e27b-29cf-41d5-8b1c-d2a3d2941755 | 24-3429 - GUCCI, BBY and BOSS - Personalization BW, Kenya | 10 | ELECTRICAL |  | Finish-to-Start (FS) | 0 | ELECTRICAL (ELECTRICAL) | Not Started (NOT_STARTED) | 8 | 0 | Generated from SPAA - MEDIUM
59c2d03f-0896-4483-bf51-346ef44a9d0f | 24-3429 - GUCCI, BBY and BOSS - Personalization BW, Kenya | 11 | PRINT |  | Finish-to-Start (FS) | 0 | PRINT (PRINT) | Not Started (NOT_STARTED) | 8 | 0 | Generated from SPAA - MEDIUM
30b7815a-5077-4c7b-9fd0-fc408ed304a3 | 24-3429 - GUCCI, BBY and BOSS - Personalization BW, Kenya | 12 | MDF FINAL PERMANENT |  | Finish-to-Start (FS) | 0 | MDF FINAL PERMANENT (MDF-FIN-PER) | Not Started (NOT_STARTED) | 8 | 0 | Generated from SPAA - MEDIUM
71c572c3-b2f7-46ef-98bc-8ef273ff3c5f | 24-3429 - GUCCI, BBY and BOSS - Personalization BW, Kenya | 13 | MDF FINAL SPAA |  | Finish-to-Start (FS) | 0 | MDF FINAL SPAA (MDF-FIN-SPA) | Not Started (NOT_STARTED) | 8 | 0 | Generated from SPAA - MEDIUM
730084aa-b0a9-41c1-b4a9-e9178285e137 | 24-3429 - GUCCI, BBY and BOSS - Personalization BW, Kenya | 14 | INSTALLATION |  | Finish-to-Start (FS) | 0 | INSTALLATION (INSTALLATION) | Not Started (NOT_STARTED) | 8 | 0
8754d361-7ca7-41ac-824b-e53b80415dde | 24-3351 - TOMFORD- KILIAN ANGOLA , FIDALGA FORTALEZA, FIDALGA AVENNIDA | 1 | PPO JOINERY |  | Finish-to-Start (FS) | 0 | PPO JOINERY (PPO-JOINERY) | Waiting (WAITING) | 8 | 7.84
e023ac2b-c112-458f-a4fc-3aa7b367aa8d | 24-3351 - TOMFORD- KILIAN ANGOLA , FIDALGA FORTALEZA, FIDALGA AVENNIDA | 2 | PPO METAL |  | Finish-to-Start (FS) | 0 | PPO METAL (PPO-METAL) | Not Started (NOT_STARTED) | 8 | 0 | Generated from SPAA-FIXED - MEDIUM
42857075-4d19-49ae-8a80-7d8960623b32 | 24-3351 - TOMFORD- KILIAN ANGOLA , FIDALGA FORTALEZA, FIDALGA AVENNIDA | 3 | MACHINE SHOP |  | Finish-to-Start (FS) | 0 | MACHINE SHOP (MACHINE-SHOP) | Not Started (NOT_STARTED) | 8 | 0 | Generated from SPAA-FIXED - MEDIUM
60c6280c-3006-4cd6-830a-264f9469f128 | 24-3351 - TOMFORD- KILIAN ANGOLA , FIDALGA FORTALEZA, FIDALGA AVENNIDA | 4 | MDF STRUCTURE PERMANENT |  | Finish-to-Start (FS) | 0 | MDF STRUCTURE PERMANENT (MDF-STR-PER) | Not Started (NOT_STARTED) | 8 | 0 | Generated from SPAA-FIXED - MEDIUM
8db9eee1-9bff-4330-9b89-86519066a511 | 24-3351 - TOMFORD- KILIAN ANGOLA , FIDALGA FORTALEZA, FIDALGA AVENNIDA | 5 | MDF STRUCTURE SPAA |  | Finish-to-Start (FS) | 0 | MDF STRUCTURE SPAA (MDF-STR-SPAA) | Not Started (NOT_STARTED) | 8 | 0 | Generated from SPAA-FIXED - MEDIUM
fa2903f1-6d8a-4c40-81d3-ad65ccc8e6f0 | 24-3351 - TOMFORD- KILIAN ANGOLA , FIDALGA FORTALEZA, FIDALGA AVENNIDA | 6 | METAL FAB |  | Finish-to-Start (FS) | 0 | METAL FAB (METAL-FAB) | Not Started (NOT_STARTED) | 8 | 0 | Generated from SPAA-FIXED - MEDIUM
a28602f8-0bc6-4353-9527-e8efa79d966b | 24-3351 - TOMFORD- KILIAN ANGOLA , FIDALGA FORTALEZA, FIDALGA AVENNIDA | 7 | METAL POLISH |  | Finish-to-Start (FS) | 0 | METAL POLISH (METAL-POLISH) | Not Started (NOT_STARTED) | 8 | 0
494e60c1-b0dd-45a7-8205-68f13abc09b1 | 24-3351 - TOMFORD- KILIAN ANGOLA , FIDALGA FORTALEZA, FIDALGA AVENNIDA | 8 | PAINT |  | Finish-to-Start (FS) | 0 | PAINT (PAINT) | Not Started (NOT_STARTED) | 8 | 0 | Generated from SPAA-FIXED - MEDIUM
ebf767d8-5c43-4d25-bf81-1970ec02ec1e | 24-3351 - TOMFORD- KILIAN ANGOLA , FIDALGA FORTALEZA, FIDALGA AVENNIDA | 9 | ACRYLIC |  | Finish-to-Start (FS) | 0 | ACRYLIC (ACRYLIC) | Not Started (NOT_STARTED) | 8 | 0 | Generated from SPAA-FIXED - MEDIUM
c5102e46-35f6-4384-8607-058b29b7705d | 24-3351 - TOMFORD- KILIAN ANGOLA , FIDALGA FORTALEZA, FIDALGA AVENNIDA | 10 | ELECTRICAL |  | Finish-to-Start (FS) | 0 | ELECTRICAL (ELECTRICAL) | Not Started (NOT_STARTED) | 8 | 0 | Generated from SPAA-FIXED - MEDIUM
a4924a5d-c9eb-4d86-808e-aaff221321f4 | 24-3351 - TOMFORD- KILIAN ANGOLA , FIDALGA FORTALEZA, FIDALGA AVENNIDA | 11 | PRINT |  | Finish-to-Start (FS) | 0 | PRINT (PRINT) | Not Started (NOT_STARTED) | 8 | 0 | Generated from SPAA-FIXED - MEDIUM
ea36408a-7603-4efe-a1dc-c667a17cfabe | 24-3351 - TOMFORD- KILIAN ANGOLA , FIDALGA FORTALEZA, FIDALGA AVENNIDA | 12 | MDF FINAL PERMANENT |  | Finish-to-Start (FS) | 0 | MDF FINAL PERMANENT (MDF-FIN-PER) | Not Started (NOT_STARTED) | 8 | 0 | Generated from SPAA-FIXED - MEDIUM
f81ab70d-4afd-47de-a025-4c3417f2bd33 | 24-3351 - TOMFORD- KILIAN ANGOLA , FIDALGA FORTALEZA, FIDALGA AVENNIDA | 13 | MDF FINAL SPAA |  | Finish-to-Start (FS) | 0 | MDF FINAL SPAA (MDF-FIN-SPA) | Not Started (NOT_STARTED) | 8 | 0 | Generated from SPAA-FIXED - MEDIUM
f72c96b5-81b1-4108-931d-9067789d2476 | 24-3351 - TOMFORD- KILIAN ANGOLA , FIDALGA FORTALEZA, FIDALGA AVENNIDA | 14 | INSTALLATION |  | Finish-to-Start (FS) | 0 | INSTALLATION (INSTALLATION) | Not Started (NOT_STARTED) | 8 | 0 | Generated from SPAA-FIXED - MEDIUM
3644893f-587e-4c6b-8c12-331b2431d193 | 24-3376 - Boss Collection Gondola - Kenya | 1 | PPO JOINERY |  | Finish-to-Start (FS) | 0 | PPO JOINERY (PPO-JOINERY) | Waiting (WAITING) | 8 | 7.84
24ab56b7-6bcb-4bd2-8b14-bf4650a30a19 | 24-3376 - Boss Collection Gondola - Kenya | 2 | PPO METAL |  | Finish-to-Start (FS) | 0 | PPO METAL (PPO-METAL) | Not Started (NOT_STARTED) | 8 | 0 | Generated from SPAA - COMPLEX
1daae0a3-803e-4b07-9c21-c2e1543de3d8 | 24-3376 - Boss Collection Gondola - Kenya | 3 | MACHINE SHOP |  | Finish-to-Start (FS) | 0 | MACHINE SHOP (MACHINE-SHOP) | Not Started (NOT_STARTED) | 8 | 0 | Generated from SPAA - COMPLEX
2e7b95fa-34d3-490d-a20c-30eda1aeb71a | 24-3376 - Boss Collection Gondola - Kenya | 4 | MDF STRUCTURE PERMANENT |  | Finish-to-Start (FS) | 0 | MDF STRUCTURE PERMANENT (MDF-STR-PER) | Not Started (NOT_STARTED) | 8 | 0 | Generated from SPAA - COMPLEX
25062bc1-d7fd-42db-9eaa-1508aa1c3ca5 | 24-3376 - Boss Collection Gondola - Kenya | 5 | MDF STRUCTURE SPAA |  | Finish-to-Start (FS) | 0 | MDF STRUCTURE SPAA (MDF-STR-SPAA) | Not Started (NOT_STARTED) | 8 | 0 | Generated from SPAA - COMPLEX
9e956450-c2d9-4b48-9333-78000aeec380 | 24-3376 - Boss Collection Gondola - Kenya | 6 | METAL FAB |  | Finish-to-Start (FS) | 0 | METAL FAB (METAL-FAB) | Not Started (NOT_STARTED) | 8 | 0 | Generated from SPAA - COMPLEX
4520373e-f84b-4057-a408-4acb7f6ed4e2 | 24-3376 - Boss Collection Gondola - Kenya | 7 | METAL POLISH |  | Finish-to-Start (FS) | 0 | METAL POLISH (METAL-POLISH) | Not Started (NOT_STARTED) | 8 | 0 | Generated from SPAA - COMPLEX
8dd35c91-21f0-4096-b88d-e5e58f26e197 | 24-3376 - Boss Collection Gondola - Kenya | 8 | PAINT |  | Finish-to-Start (FS) | 0 | PAINT (PAINT) | Not Started (NOT_STARTED) | 8 | 0 | Generated from SPAA - COMPLEX
6ce85126-dc36-4a36-a0bc-57e717477b63 | 24-3376 - Boss Collection Gondola - Kenya | 9 | ACRYLIC |  | Finish-to-Start (FS) | 0 | ACRYLIC (ACRYLIC) | Not Started (NOT_STARTED) | 8 | 0 | Generated from SPAA - COMPLEX
9198651c-0673-452c-848d-84c853d16fdb | 24-3376 - Boss Collection Gondola - Kenya | 10 | ELECTRICAL |  | Finish-to-Start (FS) | 0 | ELECTRICAL (ELECTRICAL) | Not Started (NOT_STARTED) | 8 | 0
2f34f091-1b11-4e10-b49a-ca199a0e8264 | 24-3376 - Boss Collection Gondola - Kenya | 11 | PRINT |  | Finish-to-Start (FS) | 0 | PRINT (PRINT) | Not Started (NOT_STARTED) | 8 | 0 | Generated from SPAA - COMPLEX
32ef5c62-4c8a-4396-a3e3-40b4e803da94 | 24-3376 - Boss Collection Gondola - Kenya | 12 | MDF FINAL PERMANENT |  | Finish-to-Start (FS) | 0 | MDF FINAL PERMANENT (MDF-FIN-PER) | Not Started (NOT_STARTED) | 8 | 0 | Generated from SPAA - COMPLEX
957b920a-46e5-420e-9c6d-9a06380efca5 | 24-3376 - Boss Collection Gondola - Kenya | 13 | MDF FINAL SPAA |  | Finish-to-Start (FS) | 0 | MDF FINAL SPAA (MDF-FIN-SPA) | Not Started (NOT_STARTED) | 8 | 0 | Generated from SPAA - COMPLEX
0d78f5cf-9d9a-4a4d-8ebc-aeb900cbce0e | 24-3376 - Boss Collection Gondola - Kenya | 14 | INSTALLATION |  | Finish-to-Start (FS) | 0 | INSTALLATION (INSTALLATION) | Not Started (NOT_STARTED) | 8 | 0 | Generated from SPAA - COMPLEX
2737a832-0351-40c1-a929-86d1777ca35d | 24-3388 - Gucci Counters - Areej Muscat Window | 1 | PPO JOINERY |  | Finish-to-Start (FS) | 0 | PPO JOINERY (PPO-JOINERY) | Waiting (WAITING) | 8 | 7.84
484111e9-ddf0-4169-9410-33e3daab106f | 24-3388 - Gucci Counters - Areej Muscat Window | 2 | PPO METAL |  | Finish-to-Start (FS) | 0 | PPO METAL (PPO-METAL) | Not Started (NOT_STARTED) | 8 | 0 | Generated from PERMANENT - SIMPLE
6483cb0d-fdec-49fa-a44b-cd3fe96a684c | 24-3388 - Gucci Counters - Areej Muscat Window | 3 | MACHINE SHOP |  | Finish-to-Start (FS) | 0 | MACHINE SHOP (MACHINE-SHOP) | Not Started (NOT_STARTED) | 8 | 0 | Generated from PERMANENT - SIMPLE
a4c609d4-f35b-4261-9dce-bda71a8537f2 | 24-3388 - Gucci Counters - Areej Muscat Window | 4 | MDF STRUCTURE PERMANENT |  | Finish-to-Start (FS) | 0 | MDF STRUCTURE PERMANENT (MDF-STR-PER) | Not Started (NOT_STARTED) | 8 | 0 | Generated from PERMANENT - SIMPLE
e23480fb-feae-4dbe-a5c4-11019a5ed485 | 24-3388 - Gucci Counters - Areej Muscat Window | 5 | MDF STRUCTURE SPAA |  | Finish-to-Start (FS) | 0 | MDF STRUCTURE SPAA (MDF-STR-SPAA) | Not Started (NOT_STARTED) | 8 | 0 | Generated from PERMANENT - SIMPLE
287eeb73-4b23-4e60-a6dd-b38259d3295e | 24-3388 - Gucci Counters - Areej Muscat Window | 6 | METAL FAB |  | Finish-to-Start (FS) | 0 | METAL FAB (METAL-FAB) | Not Started (NOT_STARTED) | 8 | 0 | Generated from PERMANENT - SIMPLE
3a0362a0-8a61-49f7-9d57-05e2a16889c8 | 24-3388 - Gucci Counters - Areej Muscat Window | 7 | METAL POLISH |  | Finish-to-Start (FS) | 0 | METAL POLISH (METAL-POLISH) | Not Started (NOT_STARTED) | 8 | 0 | Generated from PERMANENT - SIMPLE
a22e9e43-23a4-4615-b267-3cd744aa338d | 24-3388 - Gucci Counters - Areej Muscat Window | 8 | PAINT |  | Finish-to-Start (FS) | 0 | PAINT (PAINT) | Not Started (NOT_STARTED) | 8 | 0 | Generated from PERMANENT - SIMPLE
a8ee4e9f-aa1b-4cd1-b3d4-b30b0979e7f5 | 24-3388 - Gucci Counters - Areej Muscat Window | 9 | ACRYLIC |  | Finish-to-Start (FS) | 0 | ACRYLIC (ACRYLIC) | Not Started (NOT_STARTED) | 8 | 0 | Generated from PERMANENT - SIMPLE
fa4a5479-14c0-487b-8aa6-ddb275a22391 | 24-3388 - Gucci Counters - Areej Muscat Window | 10 | ELECTRICAL |  | Finish-to-Start (FS) | 0 | ELECTRICAL (ELECTRICAL) | Not Started (NOT_STARTED) | 8 | 0 | Generated from PERMANENT - SIMPLE
85ea972c-f1e3-4e3c-b807-9825e03cbe2e | 24-3388 - Gucci Counters - Areej Muscat Window | 11 | PRINT |  | Finish-to-Start (FS) | 0 | PRINT (PRINT) | Not Started (NOT_STARTED) | 8 | 0
4607f9ad-b4a8-4386-9389-a97e0c4dc4ca | 24-3388 - Gucci Counters - Areej Muscat Window | 12 | MDF FINAL PERMANENT |  | Finish-to-Start (FS) | 0 | MDF FINAL PERMANENT (MDF-FIN-PER) | Not Started (NOT_STARTED) | 8 | 0 | Generated from PERMANENT - SIMPLE
3d4ae840-1997-42d0-b0df-44852b757391 | 24-3388 - Gucci Counters - Areej Muscat Window | 13 | MDF FINAL SPAA |  | Finish-to-Start (FS) | 0 | MDF FINAL SPAA (MDF-FIN-SPA) | Not Started (NOT_STARTED) | 8 | 0 | Generated from PERMANENT - SIMPLE
4df9cb6a-1817-44aa-b01b-a964fdb85f88 | 24-3388 - Gucci Counters - Areej Muscat Window | 14 | INSTALLATION |  | Finish-to-Start (FS) | 0 | INSTALLATION (INSTALLATION) | Not Started (NOT_STARTED) | 8 | 0 | Generated from PERMANENT - SIMPLE

## Dropdown Values (hidden)
project_id | predecessor_stage_id | dependency_type | department_code | workflow_status
24-2543 - Berluti Facade - MOE | 24-3078 - Pernod Ricard deal, Bahrain Duty Free ¦ 1. PPO JOINERY | Finish-to-Start (FS) | PPO JOINERY (PPO-JOINERY) | Not Started (NOT_STARTED)
24-3078 - Pernod Ricard deal, Bahrain Duty Free | 24-2543 - Berluti Facade - MOE ¦ 1. PPO JOINERY |  | PPO METAL (PPO-METAL) | Ready (READY)
24-3211 - BVLGARI ghana Accra Scentopia | 24-3429 - GUCCI, BBY and BOSS - Personalization BW, Kenya ¦ 1. PPO JOINERY |  | MACHINE SHOP (MACHINE-SHOP) | In Progress (IN_PROGRESS)
24-3212 - Bvlari_GHANA Accra Scentopia Kempinski | 24-3239 - EL- CL - ZINO CAP SUD, IVORY COAST ¦ 1. PPO JOINERY |  | MDF STRUCTURE PERMANENT (MDF-STR-PER) | Waiting (WAITING)
24-3239 - EL- CL - ZINO CAP SUD, IVORY COAST | 24-3351 - TOMFORD- KILIAN ANGOLA , FIDALGA FORTALEZA, FIDALGA AVENNIDA ¦ 1. PPO JOINERY |  | MDF STRUCTURE SPAA (MDF-STR-SPAA) | Complete (COMPLETE)
24-3351 - TOMFORD- KILIAN ANGOLA , FIDALGA FORTALEZA, FIDALGA AVENNIDA | 24-3211 - BVLGARI ghana Accra Scentopia ¦ 1. PPO JOINERY |  | METAL FAB (METAL-FAB) | Skipped (SKIPPED)
24-3365 - PEN_T3 SHOP 700 Egypt_30th AUG | 24-3376 - Boss Collection Gondola - Kenya ¦ 1. PPO JOINERY |  | METAL POLISH (METAL-POLISH)
24-3376 - Boss Collection Gondola - Kenya | 24-3365 - PEN_T3 SHOP 700 Egypt_30th AUG ¦ 1. PPO JOINERY |  | PAINT (PAINT)
24-3388 - Gucci Counters - Areej Muscat Window | 24-3388 - Gucci Counters - Areej Muscat Window ¦ 1. PPO JOINERY |  | ACRYLIC (ACRYLIC)
24-3429 - GUCCI, BBY and BOSS - Personalization BW, Kenya | 24-3212 - Bvlari_GHANA Accra Scentopia Kempinski ¦ 1. PPO JOINERY |  | ELECTRICAL (ELECTRICAL)
| 24-3211 - BVLGARI ghana Accra Scentopia ¦ 2. PPO METAL |  | PRINT (PRINT)
| 24-3078 - Pernod Ricard deal, Bahrain Duty Free ¦ 2. PPO METAL |  | MDF FINAL PERMANENT (MDF-FIN-PER)
| 24-3212 - Bvlari_GHANA Accra Scentopia Kempinski ¦ 2. PPO METAL |  | MDF FINAL SPAA (MDF-FIN-SPA)
| 24-3351 - TOMFORD- KILIAN ANGOLA , FIDALGA FORTALEZA, FIDALGA AVENNIDA ¦ 2. PPO METAL |  | INSTALLATION (INSTALLATION)
24-3376 - Boss Collection Gondola - Kenya ¦ 2. PPO METAL
24-3239 - EL- CL - ZINO CAP SUD, IVORY COAST ¦ 2. PPO METAL
24-3429 - GUCCI, BBY and BOSS - Personalization BW, Kenya ¦ 2. PPO METAL
24-3365 - PEN_T3 SHOP 700 Egypt_30th AUG ¦ 2. PPO METAL
24-3388 - Gucci Counters - Areej Muscat Window ¦ 2. PPO METAL
24-2543 - Berluti Facade - MOE ¦ 2. PPO METAL
24-3351 - TOMFORD- KILIAN ANGOLA , FIDALGA FORTALEZA, FIDALGA AVENNIDA ¦ 3. MACHINE SHOP
24-3211 - BVLGARI ghana Accra Scentopia ¦ 3. MACHINE SHOP
24-2543 - Berluti Facade - MOE ¦ 3. MACHINE SHOP
24-3239 - EL- CL - ZINO CAP SUD, IVORY COAST ¦ 3. MACHINE SHOP
24-3429 - GUCCI, BBY and BOSS - Personalization BW, Kenya ¦ 3. MACHINE SHOP
24-3212 - Bvlari_GHANA Accra Scentopia Kempinski ¦ 3. MACHINE SHOP
24-3388 - Gucci Counters - Areej Muscat Window ¦ 3. MACHINE SHOP
24-3376 - Boss Collection Gondola - Kenya ¦ 3. MACHINE SHOP
24-3365 - PEN_T3 SHOP 700 Egypt_30th AUG ¦ 3. MACHINE SHOP
24-3078 - Pernod Ricard deal, Bahrain Duty Free ¦ 3. MACHINE SHOP
24-3365 - PEN_T3 SHOP 700 Egypt_30th AUG ¦ 4. MDF STRUCTURE PERMANENT
24-3239 - EL- CL - ZINO CAP SUD, IVORY COAST ¦ 4. MDF STRUCTURE PERMANENT
24-3376 - Boss Collection Gondola - Kenya ¦ 4. MDF STRUCTURE PERMANENT
24-2543 - Berluti Facade - MOE ¦ 4. MDF STRUCTURE PERMANENT
24-3078 - Pernod Ricard deal, Bahrain Duty Free ¦ 4. MDF STRUCTURE PERMANENT
24-3429 - GUCCI, BBY and BOSS - Personalization BW, Kenya ¦ 4. MDF STRUCTURE PERMANENT
24-3351 - TOMFORD- KILIAN ANGOLA , FIDALGA FORTALEZA, FIDALGA AVENNIDA ¦ 4. MDF STRUCTURE PERMANENT
24-3211 - BVLGARI ghana Accra Scentopia ¦ 4. MDF STRUCTURE PERMANENT
24-3212 - Bvlari_GHANA Accra Scentopia Kempinski ¦ 4. MDF STRUCTURE PERMANENT
24-3388 - Gucci Counters - Areej Muscat Window ¦ 4. MDF STRUCTURE PERMANENT
24-3078 - Pernod Ricard deal, Bahrain Duty Free ¦ 5. MDF STRUCTURE SPAA
24-3211 - BVLGARI ghana Accra Scentopia ¦ 5. MDF STRUCTURE SPAA
24-3212 - Bvlari_GHANA Accra Scentopia Kempinski ¦ 5. MDF STRUCTURE SPAA
24-3365 - PEN_T3 SHOP 700 Egypt_30th AUG ¦ 5. MDF STRUCTURE SPAA
24-3239 - EL- CL - ZINO CAP SUD, IVORY COAST ¦ 5. MDF STRUCTURE SPAA
24-3351 - TOMFORD- KILIAN ANGOLA , FIDALGA FORTALEZA, FIDALGA AVENNIDA ¦ 5. MDF STRUCTURE SPAA
24-3429 - GUCCI, BBY and BOSS - Personalization BW, Kenya ¦ 5. MDF STRUCTURE SPAA
24-3388 - Gucci Counters - Areej Muscat Window ¦ 5. MDF STRUCTURE SPAA
24-3376 - Boss Collection Gondola - Kenya ¦ 5. MDF STRUCTURE SPAA
24-2543 - Berluti Facade - MOE ¦ 5. MDF STRUCTURE SPAA
24-3211 - BVLGARI ghana Accra Scentopia ¦ 6. METAL FAB
24-3365 - PEN_T3 SHOP 700 Egypt_30th AUG ¦ 6. METAL FAB
24-3239 - EL- CL - ZINO CAP SUD, IVORY COAST ¦ 6. METAL FAB
24-3078 - Pernod Ricard deal, Bahrain Duty Free ¦ 6. METAL FAB
24-3351 - TOMFORD- KILIAN ANGOLA , FIDALGA FORTALEZA, FIDALGA AVENNIDA ¦ 6. METAL FAB
24-3388 - Gucci Counters - Areej Muscat Window ¦ 6. METAL FAB
24-3376 - Boss Collection Gondola - Kenya ¦ 6. METAL FAB
24-3212 - Bvlari_GHANA Accra Scentopia Kempinski ¦ 6. METAL FAB
24-2543 - Berluti Facade - MOE ¦ 6. METAL FAB
24-3429 - GUCCI, BBY and BOSS - Personalization BW, Kenya ¦ 6. METAL FAB
24-3239 - EL- CL - ZINO CAP SUD, IVORY COAST ¦ 7. METAL POLISH
24-3351 - TOMFORD- KILIAN ANGOLA , FIDALGA FORTALEZA, FIDALGA AVENNIDA ¦ 7. METAL POLISH
24-3429 - GUCCI, BBY and BOSS - Personalization BW, Kenya ¦ 7. METAL POLISH
24-3078 - Pernod Ricard deal, Bahrain Duty Free ¦ 7. METAL POLISH
24-3365 - PEN_T3 SHOP 700 Egypt_30th AUG ¦ 7. METAL POLISH
24-3388 - Gucci Counters - Areej Muscat Window ¦ 7. METAL POLISH
24-3211 - BVLGARI ghana Accra Scentopia ¦ 7. METAL POLISH
24-3212 - Bvlari_GHANA Accra Scentopia Kempinski ¦ 7. METAL POLISH
24-3376 - Boss Collection Gondola - Kenya ¦ 7. METAL POLISH
24-2543 - Berluti Facade - MOE ¦ 7. METAL POLISH
24-3388 - Gucci Counters - Areej Muscat Window ¦ 8. PAINT
24-3211 - BVLGARI ghana Accra Scentopia ¦ 8. PAINT
24-2543 - Berluti Facade - MOE ¦ 8. PAINT
24-3078 - Pernod Ricard deal, Bahrain Duty Free ¦ 8. PAINT
24-3365 - PEN_T3 SHOP 700 Egypt_30th AUG ¦ 8. PAINT
24-3239 - EL- CL - ZINO CAP SUD, IVORY COAST ¦ 8. PAINT
24-3351 - TOMFORD- KILIAN ANGOLA , FIDALGA FORTALEZA, FIDALGA AVENNIDA ¦ 8. PAINT
24-3429 - GUCCI, BBY and BOSS - Personalization BW, Kenya ¦ 8. PAINT
24-3212 - Bvlari_GHANA Accra Scentopia Kempinski ¦ 8. PAINT
24-3376 - Boss Collection Gondola - Kenya ¦ 8. PAINT
24-3429 - GUCCI, BBY and BOSS - Personalization BW, Kenya ¦ 9. ACRYLIC
24-3239 - EL- CL - ZINO CAP SUD, IVORY COAST ¦ 9. ACRYLIC
24-3351 - TOMFORD- KILIAN ANGOLA , FIDALGA FORTALEZA, FIDALGA AVENNIDA ¦ 9. ACRYLIC
24-3212 - Bvlari_GHANA Accra Scentopia Kempinski ¦ 9. ACRYLIC
24-3376 - Boss Collection Gondola - Kenya ¦ 9. ACRYLIC
24-3078 - Pernod Ricard deal, Bahrain Duty Free ¦ 9. ACRYLIC
24-3211 - BVLGARI ghana Accra Scentopia ¦ 9. ACRYLIC
24-3388 - Gucci Counters - Areej Muscat Window ¦ 9. ACRYLIC
24-3365 - PEN_T3 SHOP 700 Egypt_30th AUG ¦ 9. ACRYLIC
24-2543 - Berluti Facade - MOE ¦ 9. ACRYLIC
24-3365 - PEN_T3 SHOP 700 Egypt_30th AUG ¦ 10. ELECTRICAL
24-2543 - Berluti Facade - MOE ¦ 10. ELECTRICAL
24-3212 - Bvlari_GHANA Accra Scentopia Kempinski ¦ 10. ELECTRICAL
24-3388 - Gucci Counters - Areej Muscat Window ¦ 10. ELECTRICAL
24-3376 - Boss Collection Gondola - Kenya ¦ 10. ELECTRICAL
24-3429 - GUCCI, BBY and BOSS - Personalization BW, Kenya ¦ 10. ELECTRICAL
24-3211 - BVLGARI ghana Accra Scentopia ¦ 10. ELECTRICAL
24-3239 - EL- CL - ZINO CAP SUD, IVORY COAST ¦ 10. ELECTRICAL
24-3351 - TOMFORD- KILIAN ANGOLA , FIDALGA FORTALEZA, FIDALGA AVENNIDA ¦ 10. ELECTRICAL
24-3078 - Pernod Ricard deal, Bahrain Duty Free ¦ 10. ELECTRICAL
24-3429 - GUCCI, BBY and BOSS - Personalization BW, Kenya ¦ 11. PRINT
24-2543 - Berluti Facade - MOE ¦ 11. PRINT
24-3351 - TOMFORD- KILIAN ANGOLA , FIDALGA FORTALEZA, FIDALGA AVENNIDA ¦ 11. PRINT
24-3388 - Gucci Counters - Areej Muscat Window ¦ 11. PRINT
24-3078 - Pernod Ricard deal, Bahrain Duty Free ¦ 11. PRINT
24-3211 - BVLGARI ghana Accra Scentopia ¦ 11. PRINT
24-3365 - PEN_T3 SHOP 700 Egypt_30th AUG ¦ 11. PRINT
24-3212 - Bvlari_GHANA Accra Scentopia Kempinski ¦ 11. PRINT
24-3376 - Boss Collection Gondola - Kenya ¦ 11. PRINT
24-3239 - EL- CL - ZINO CAP SUD, IVORY COAST ¦ 11. PRINT
24-3212 - Bvlari_GHANA Accra Scentopia Kempinski ¦ 12. MDF FINAL PERMANENT
24-2543 - Berluti Facade - MOE ¦ 12. MDF FINAL PERMANENT
24-3429 - GUCCI, BBY and BOSS - Personalization BW, Kenya ¦ 12. MDF FINAL PERMANENT
24-3365 - PEN_T3 SHOP 700 Egypt_30th AUG ¦ 12. MDF FINAL PERMANENT
24-3351 - TOMFORD- KILIAN ANGOLA , FIDALGA FORTALEZA, FIDALGA AVENNIDA ¦ 12. MDF FINAL PERMANENT
24-3376 - Boss Collection Gondola - Kenya ¦ 12. MDF FINAL PERMANENT
24-3388 - Gucci Counters - Areej Muscat Window ¦ 12. MDF FINAL PERMANENT
24-3239 - EL- CL - ZINO CAP SUD, IVORY COAST ¦ 12. MDF FINAL PERMANENT
24-3078 - Pernod Ricard deal, Bahrain Duty Free ¦ 12. MDF FINAL PERMANENT
24-3211 - BVLGARI ghana Accra Scentopia ¦ 12. MDF FINAL PERMANENT
24-3365 - PEN_T3 SHOP 700 Egypt_30th AUG ¦ 13. MDF FINAL SPAA
24-2543 - Berluti Facade - MOE ¦ 13. MDF FINAL SPAA
24-3078 - Pernod Ricard deal, Bahrain Duty Free ¦ 13. MDF FINAL SPAA
24-3429 - GUCCI, BBY and BOSS - Personalization BW, Kenya ¦ 13. MDF FINAL SPAA
24-3211 - BVLGARI ghana Accra Scentopia ¦ 13. MDF FINAL SPAA
24-3239 - EL- CL - ZINO CAP SUD, IVORY COAST ¦ 13. MDF FINAL SPAA
24-3376 - Boss Collection Gondola - Kenya ¦ 13. MDF FINAL SPAA
24-3212 - Bvlari_GHANA Accra Scentopia Kempinski ¦ 13. MDF FINAL SPAA
24-3388 - Gucci Counters - Areej Muscat Window ¦ 13. MDF FINAL SPAA
24-3351 - TOMFORD- KILIAN ANGOLA , FIDALGA FORTALEZA, FIDALGA AVENNIDA ¦ 13. MDF FINAL SPAA
24-3429 - GUCCI, BBY and BOSS - Personalization BW, Kenya ¦ 14. INSTALLATION
24-3239 - EL- CL - ZINO CAP SUD, IVORY COAST ¦ 14. INSTALLATION
24-3212 - Bvlari_GHANA Accra Scentopia Kempinski ¦ 14. INSTALLATION
24-3211 - BVLGARI ghana Accra Scentopia ¦ 14. INSTALLATION
24-3351 - TOMFORD- KILIAN ANGOLA , FIDALGA FORTALEZA, FIDALGA AVENNIDA ¦ 14. INSTALLATION
24-2543 - Berluti Facade - MOE ¦ 14. INSTALLATION
24-3376 - Boss Collection Gondola - Kenya ¦ 14. INSTALLATION
24-3365 - PEN_T3 SHOP 700 Egypt_30th AUG ¦ 14. INSTALLATION
24-3078 - Pernod Ricard deal, Bahrain Duty Free ¦ 14. INSTALLATION
24-3388 - Gucci Counters - Areej Muscat Window ¦ 14. INSTALLATION

## Export Info
Field | Value
Module | Project Workflow Stages
Exported At | 2026-06-18T09:05:09.550Z
Search Filter | None
Row Count | 140